## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0 | [9 empty] | Instruction to use the lessons learned document template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.
PROJECT NAME | Cloud Events
PROJECT ID
PROJECT MANAGER | Jayanth G S
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 22/06/20 | The employee preferences are considered for both Event1 and Event2 and both. Classification model to be implemented could be applied for both of the at same time or differently. | Technical | None | Separate classification is preferrable as the entity groups formed are rather quite distinct. | Separate model classifications. | Project Team Lead | Closed
2 | 25/07/20 | Machine Learning algorithm to be applied only for Domain and Event Extraction. Normal matching algorithm for employee names extraction from data set. | Technical, Workgroup Discussion | None | Machine Learning approach to be applied for employee extraction along with domain extraction. | After acquiring domain and events type, ML approach is used to acquire employee names. | Project Team Lead, Project Manager | Closed
3 | 16/7/20 | Classification model's prediction for a certain input consists of more than one output i.e. many employees might be interested for a single event. | Technical | A single output was provided for an instance where multiple were expected. | Append all the employee names obtained from classifier model for a single event. | Model is programmed to output employee names based on the probability percentage. A certain percentage criteria is needed for the employee to be recommended the event. | Project Team Lead | Closed
4 | 14/7/2020 | Algorithm for classification for employees based on extracted domains and event type. | Technical | Various models were applied such as KMeans, Random Forest,etc however performance was not up to the mark. | A suitable model was needed to be selected ASAP to be on par with project plan. | Decision Tree proved to be quite reliable model for this problem. | Project Team Lead | Closed
5 | 26/06/20 | NLP applied using BoW method hence dictionaries used for vectorizer are really big and decreases code readability. | Technical | The code cells content were too large and not appropriate for code readability. | Dictionaries to be stored within the project directory as files so that the they can be accessed whenever required. | DIctionaries are stored as Pickle files. | Project Team Lead | Closed
6 | 27/07/20 | BoW required input data clearing before using vectorizer function | Technical | The keywords for a domain or an event were too many and its interpretition to the model was vague which faltered the model accuracy. | The words that don't contribute to model accuracy should be removed. | Stop-Words and re function implementation. | Project Team Lead | Closed