## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Cloud Events
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 15/06/2020
EXPECTED COMPLETION DATE | 31/07/2020
ESTIMATED COST | 0
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | The main objective of the project is to develop an Event Recommendation system for the employees of a Cloud Counselage based on the records of their preferences record available to us in a data set.
BUSINESS CASE | In this era, the corporate world is inculcated in extensive programmes for their employees to have the potential to promote creativity and productivity. The task of recommending every eligible employee in the company regarding an event that is to be organized is sometimes waste of resources and time. To improve this task we build a model to recommend company events which is more likely to be preferred by a certain employee.
GOALS/METRICS | To create a reliable recommedation system for the company employees to notify them about upcoming events based on their preferences.
EXPECTED DELIVERABLES | An Excel sheet which will output the names of employees to whom a certain event needs to be recommended.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Employee domains and event types are extracted from input events using a ML approach and then they are recommended to the employees with matching preference.
OUTSIDE OF SCOPE
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Siddhesh Kadam
SUPPORT RESOURCES | Laptops, Internet Connectivity.
COST ALLOCATION | 0
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER | Siddhesh Kadam
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Scope Risk (Scope Creep) : The model will require updation in data once a new employee is hired or if an employee leaves the company. Technology Risk: The event preferences for the employees of the company are to be needed within an appropriate range of number for the project model to work on. The appropriate selection of machine learning algorithm for recommendation of events.
ASSUMPTIONS | Cloud Events will help notify employees of the company of their preferred upcoming events.
CONSTRAINTS | Very small dataset with a lot of unique instances.