## PROJECT PLAN
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Cloud Events
PROJECT MANAGER | Jayanth G S
PROJECT DELIVERABLE | Event Recommendation System
PROJECT SCOPE | To create a reliable recommedation system for the company employees to
notify them about upcoming events based on their preferences.
PROJECT START DATE | 15/06/2020
PROJECT END DATE | 31/07/2020
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | [1] Week: 1 - Understanding Project Development and Problem Statement
| 1.1 To understand the Software Development Life Cycle (SDLC). | Siddhesh Kadam | 2020-06-15 | 2020-06-17 | 2 | COMPLETED
| 1.2 To understand the Internship Program Project Problem Statement. | Siddhesh Kadam | 2020-06-15 | 2020-06-16 | 1 | COMPLETED
| 1.3 To understand the IP - Project Methodology | Siddhesh Kadam | 2020-06-15 | 2020-06-20 | 5 | COMPLETED
2 | [2] Week: 2 - Working on different documentations of project.
| 2.1 Project Charter for summarized documentation of project. | Siddhesh Kadam | 2020-06-22 | 2020-06-26 | 4 | COMPLETED
| 2.2 Create an illustrative project report document. | Siddhesh Kadam | 2020-06-22 | 2020-06-27 | 5 | COMPLETED
| 2.3 Software Resource Specification document for project | Siddhesh Kadam | 2020-06-22 | 2020-06-26 | 4 | COMPLETED
3 | [3] Week: 3 - Working on different documentations of project.
| 3.1 Creating a Project Plan and following it thoroughly | Siddhesh Kadam | 2020-06-29 | 2020-07-02 | 3 | COMPLETED
4 | [4] Week: 4 - Development Phase
| 4.1 Creating and Maintaing a RAID log document | Siddhesh Kadam | 2020-07-06 | 2020-07-11 | 5 | COMPLETED
| 4.2 Creating and Maintaing a Development log document | Siddhesh Kadam | 2020-07-06 | 2020-07-12 | 6 | COMPLETED
4.3 Project Development
| 4.3.1 Data Cleaning and Analyzing | Siddhesh Kadam | 2020-07-06 | 2020-07-08 | 2 | COMPLETED
| 4.3.2 Visualizing data and interpreting correlations | Siddhesh Kadam | 2020-07-08 | 2020-07-10 | 2 | COMPLETED
| 4.3.3 Solution for processing events and employee domains from input | Siddhesh Kadam | 2020-07-10 | 2020-07-13 | 3 | COMPLETED
5 | [5] Week: 5 - Development Phase
5.1 Project Development
| 5.1.1 Figuring suitable M.L. model for project and preparing its features | Siddhesh Kadam | 2020-07-13 | 2020-07-13 | 0 | COMPLETED
and target values
6 | [6] Week: 6 - Development Phase
| 6.1 Creation of NLP models for Domain and Event extraction from input. | Siddhesh Kadam | 2020-07-20 | 2020-07-26 | 6 | COMPLETED
| 6.2 Increasing model accuracy. | Siddhesh Kadam | 2020-07-23 | 2020-07-27 | 4 | COMPLETED
| 6.3 Addition of input extraction from CSV file feature. | Siddhesh Kadam | 2020-07-27 | 2020-07-27 | 0 | COMPLETED
7 | [7] Week: 7 - Development Phase
| 7.1 Completion of the ML model and presenting the output in an excel sheet. | Siddhesh Kadam | 2020-07-27 | 2020-07-29 | 2 | COMPLETED