## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 1 | 0 | 1 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Cloud Events |  | Project Id: |  | Project Manager: | Jayanth G S |  |  | Assumption | 1 | 0 | 1 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 2 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 27/7/20 | Project Team Lead: | SIddhesh Kadam |  |  | Dependency | 1 | 0 | 0 | 1 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 7 |  |  |  |  | 6
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Lack of clarity in problem statement regarding ML implementation for recommendation system. | Falter in development phase. | A clear consistent problem statement with proper example output. | Project Manager | Critical |  | Open
2 | Risk | Inability to maintain and update new employee database. | Impact on the project performance. | Have a dedicated maintenance team for the project . | Project Manager | High |  | Open | Risk
3 | Risk | Events involving with multiple domain and events in a single instant. | Different domains within a single instant would me missed out. | Make a proper arrangement of all domains involved in an event. | Project Team Lead | High |  | Closed
4 | Assumption | Limitation on different number of event domain words in the input to the program at an instance. | Too many events in a single instance can disrupt the recommendations. | A feature is provided in the project for which there are certain amounts of events that can be given as inputs to the program as different instances. | Project Team Lead | High |  | Open | Assumption
5 | Risk | Data is insufficiently robust to support data analysis and performance reporting | Decrease in the accuracy of the model due to noise and overfitting. | The event preferences of the employees should be concise and not too domain specific i.e. they should have enough flexibility in options to choose their event preferences. | Project Manager | Low |  | Open | Issue
6 | Issue | No flexibility in recommending events to employees for which they have not given preference for similar events i.e. Artificial Intelligence and Machine Learning. | Events ecommendation would be undoubtedly be robust though recommendation genre type will be monotonous. | SImilar events to be open for recommendation system for suggestion to the employees. | Project Manager | Moderate |  | Open | Dependency
7 | Issue | If there is no suitable employee for an event in our data, the recommendation system based on its classification model will recommend employee of the same domain but different event preferences. | Employees receiving these recommendations may or may not be interested in the events even if they are similar to their preferences. | Overfitting the Classification model. | Project Team Lead | Moderate |  | Open
8 | Dependency | NLP for domain and events extraction from input would be captured by the model if they are closely related. | Seminars and Talks would can be used interchangebly for some extent. Same is the case for a technical fests and an expos. | Overfitting the NLP model. | Project Team Lead | Moderate |  | Open | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24